## INSTRUCTIONS
Risks, Assumptions, Constraints and Issues Log
RISKS:
Conduct a risk management session and document your results here. The client should also participate, in a separate meeting or with the whole team. In mature project management offices, a Risk Management Plan is clearly defined. We will not formalize the process beyond the steps identified here.
STEPS
1. | Identify and throughly describe the risk [columns C-D]
2. | Qualify the risk. Assign its impact and probability. Severity is a calculated field. [columns E-H]
3. | Define a response strategy. [columns I-L]
RESOURCES
Several resources are provided on the dashboard. A library or internet search will yield plenty of resources as well.
ABOUT THE SHEET
Several columns have data validation in place. Manage this as you like.
The Impact, Probability and Severity columns also have conditional formatting
CONSTRAINTS - ASSUMPTIONS
Document constraints and assumptions in order to set expectations with the client, faculty advisor, and team members. The simplist way to document assumptions is through a brainstorming session. Be sure to use keywords to trigger thoughts and ideas. Constaints are something that must be adhered to while assumptions are an agreement or understanding about the state of project characteristics.
Here are some examples:
- Technology. The technical context of the project such as platforms and environments that will be used.
- Facilities
- Resources
- Architecture & Design
- Business or client assumptions
- Financial
- Methodology & Standards
NOTE - the exercise of defining constraints and assumptions often reveals additional project risk, project management requirements or product scope
ISSUES:
Log issues and necessary actions as they come up during the project. An issue is an unforeseen event that is affection the progress of the project and requires some attention. In mature project management offices, an Issue Management Plan may be documented but we will not formalize the process here.
Bear in mind, issues may be risk triggers and already have a defined response. Issues, if severe enough, may impact the schedule, scope and budget thereby requiring a change request, assessment and approval.

## RISKS
RISK LOG
ID | Current Status | Risk Description | Project Impact | IMPACT | PROBABILITY | SEVERITY | Risk Area | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
Ex. | OPEN | Team member doesn't complete assignments. | missed milestones, poor quality deliverable, lower team grade | MED | MED | YELLOW | Schedule | non-attendance, non-communication, missed deliverables | CONTINGENCY | select my team wisely, agree on risk response in the Team Charter | proceed without the resource inform the instructor
A1 | OPEN | IT server or library does not give permission to access cmx system, which the system we are going to rely on to get the position of user. | need to find the new way to locate device, or change to the solution of M3 mapper (not responsible and precise right now) | HIGH | MED | RED | Data/Information | not secure use of cmx system | TRANSFER | Change the system of locating device | Assume we have such position data, and work on navigation portion
A2 | OPEN | Mobile device may not handle the computing of navigation and searching item based on local data (all computation is planning to be finished loclally). | Not valubale mobile app | HIGH | MED | RED | Product Quality | Low optimization skill on mobile device (IOS, Android) | AVOIDANCE | Avoid heavy task of computing on smart phones | Move the most resources-required task from personal device to a server, such as find the shortest path of navigating.

## CONSTRAINTS-ASSUMPTIONS
Assumption: |  | A belief you hold as true now or in the future.
Constraints: |  | Any restriction that defines a project's limitations. The scope, for example, is the limit of what the project is expected to accomplish but is documented thoroughly in another project artifact.
NBR | Type | Category | Description
Ex | A | Technology | programming language will be C#
Ex | A | Technology
1 | C | Data/Information | Book information need be collected by ourself.
2 | A | Technology | Programming language will be C#
3 | A | Technology | Will use Python to collect data from library wesite
4 | A | Cost | Will use more time since the group need to check each bookshelf for collecting information
5 | A | Dependencies | Depends on M3 Mapper technology
6 | A | Product Quality | The product will run on phone well and adapt to diferent type of platform.
7 | A | Project Quality | For this semester, the project will have a basic frame.
8 | C | Schedule | developing time is limited
9 | C | Privacy | Due to privacy reasons, it is difficult to get complete user data (such as MAC address).
10 | C | Cost | To develop on different platform, the group members need cost time to learn related knowledge
11 | C | Technology | Since the data collector need use WIFI-wireless, the users who not connected to the wifi will not able to use. And only campus factily and students can use it.

## ISSUES
ISSUE LOG
NBR | Category | Description | Raised By | Priority | Assigned to | Resolution | Comments
DA1 | Data/Information | Cannot find the data of book | A1 | HIGH | TM1 | TM1 will use Python to collect the data.
DA2 | Data/Information | Cannot find information of bookshelves | A2 | HIGH | TM2 | TM2 will check the information of each bookshelf and record it

## DATA_VAL
- Update the lists to reflect the options you'd like available in the different tabs.
- Each list is defined as a named range and the range name is used for data validation in each of the sheets.
Risk Area | Assessment | Response | Priority | Stakeholders
Cost | LOW | ACCEPTANCE | LOW | TM1
Data/Information | MED | AVOIDANCE | MED | TM2
Dependencies | HIGH | CONTINGENCY | HIGH | TM3
Overall Project Failure |  | MITIGATION |  | TM4
Privacy |  | TRANSFER
Product Quality
Project Quality
Resources
Schedule
Scope
Technology