## INSTRUCTIONS
Risks, Assumptions, Constraints and Issues Log
RISKS:
Conduct a risk management session and document your results here. The client should also participate, in a separate meeting or with the whole team. In mature project management offices, a Risk Management Plan is clearly defined. We will not formalize the process beyond the steps identified here.
STEPS
1. | Identify and throughly describe the risk [columns C-D]
2. | Qualify the risk. Assign its impact and probability. Severity is a calculated field. [columns E-H]
3. | Define a response strategy. [columns I-L]
RESOURCES
Several resources are provided on the dashboard. A library or internet search will yield plenty of resources as well.
ABOUT THE SHEET
Several columns have data validation in place. Manage this as you like.
The Impact, Probability and Severity columns also have conditional formatting
CONSTRAINTS - ASSUMPTIONS
Document constraints and assumptions in order to set expectations with the client, faculty advisor, and team members. The simplist way to document assumptions is through a brainstorming session. Be sure to use keywords to trigger thoughts and ideas. Constaints are something that must be adhered to while assumptions are an agreement or understanding about the state of project characteristics.
Here are some examples:
- Technology. The technical context of the project such as platforms and environments that will be used.
- Facilities
- Resources
- Architecture & Design
- Business or client assumptions
- Financial
- Methodology & Standards
NOTE - the exercise of defining constraints and assumptions often reveals additional project risk, project management requirements or product scope
ISSUES:
Log issues and necessary actions as they come up during the project. An issue is an unforeseen event that is affection the progress of the project and requires some attention. In mature project management offices, an Issue Management Plan may be documented but we will not formalize the process here.
Bear in mind, issues may be risk triggers and already have a defined response. Issues, if severe enough, may impact the schedule, scope and budget thereby requiring a change request, assessment and approval.

## RISKS
RISK LOG
ID | Current Status | Risk Description | Project Impact | IMPACT | PROBABILITY | SEVERITY | Risk Area | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
Ex. | OPEN | Team member doesn't complete assignments. | missed milestones, poor quality deliverable, lower team grade | MED | MED | YELLOW | Schedule | non-attendance, non-communication, missed deliverables | CONTINGENCY | select my team wisely, agree on risk response in the Team Charter | proceed without the resource inform the instructor
|  |  |  | MED | LOW | GREEN

## CONSTRAINTS-ASSUMPTIONS
Assumption: |  | A belief you hold as true now or in the future.
Constraints: |  | Any restriction that defines a project's limitations. The scope, for example, is the limit of what the project is expected to accomplish but is documented thoroughly in another project artifact.
NBR | Type | Category | Description
Ex | A | Technology | programming language will be C#
Ex | A | Technology

## ISSUES
ISSUE LOG
NBR | Category | Description | Raised By | Priority | Assigned to | Resolution | Comments
1

## DATA_VAL
- Update the lists to reflect the options you'd like available in the different tabs.
- Each list is defined as a named range and the range name is used for data validation in each of the sheets.
Risk Area | Assessment | Response | Priority | Stakeholders
Cost | LOW | ACCEPTANCE | LOW | TM1
Data/Information | MED | AVOIDANCE | MED | TM2
Dependencies | HIGH | CONTINGENCY | HIGH | TM3
Overall Project Failure |  | MITIGATION |  | TM4
Privacy |  | TRANSFER
Product Quality
Project Quality
Resources
Schedule
Scope
Technology